## product -Bcklog
VIRTUAL SHOPPING ANALYSIS ON LAVIE BAGS
PRODUCT - BACKLOG
id | User story | Priority | Sprint | Acceptance criteria | Notes | Status | story points
1 | As a customer, I want to browse a catalog of Lavie bags online so that I can view the collection. | High | Sprint 1 | The catalog displays all bags with images, descriptions, and prices. | Include filtering by category. | Completed | 5
2 | As a customer, I want to add items to a wishlist so that I can save bags I like for later. | Medium | Sprint 2 | Wishlist functionality works, and saved items are accessible. | Add "Login" to save wishlist. | Completed | 3
3 | As a customer, I want to make secure online payments so that I can purchase bags safely. | High | Sprint 3 | Payment gateway integrates without errors; transactions are confirmed. | Integrate with Razorpay/PayU. | Completed | 8
4 | As a customer, I want to see product reviews so that I can make informed decisions. | Medium | Sprint 4 | Reviews display on the product page with an option to add a review. | Moderate reviews before posting. | Not Completed | 5
5 | As a customer, I want live shopping events where I can interact with hosts showcasing the bags. | High | Sprint 3 | Live event page streams smoothly and includes purchase links. | Enable Q&A during live events. | Completed | 8
6 | As a customer, I want free shipping for orders over ₹1,000 so that I save on shipping costs. | Low | Sprint 4 | Shipping discounts automatically apply at checkout for eligible orders. | Show free shipping on product pages. | Completed | 3
7 | As a business, I want analytics dashboards so that I can track sales and customer engagement. | High | Sprint 4 | Dashboard includes data on sales, most-viewed products, and user activity. | Use Google Analytics integration. | Completed | 8
8 | As a customer, I want to search for specific bags by keywords so that I can find what I need. | High | Sprint 1 | Search results accurately display relevant products based on keywords. | Include advanced filters. | Completed | 5
9 | As a business, I want to manage inventory easily so that I can ensure products stay in stock. | High | Sprint 2 | Inventory dashboard updates in real-time and alerts for low stock. | Add product auto-restock options. | Completed | 8
10 | As a customer, I want influencer recommendations so that I trust the product quality. | Medium | Sprint 3 | Influencer content appears on product pages and in social media sections. | Link to influencer videos/posts. | Not Completed | 5

## Developers salary
Developers Salary Details
| Sprint | Month | Software Developer | Hardware Developer | QA Engineer | DevOps Engineer | Full-Stack Engineer
| Sprint 1 | Jan | 31027.2 | 31027.2 | 31027.2 | 31027.2 | 31027.2
| Sprint 2 | Jan | 30689 | 30689 | 30689 | 30689 | 30689
| Sprint 3 | Feb | 29820.2 | 29820.2 | 29820.2 | 29820.2 | 29820.2
| Sprint 4 | Feb | 30527.8 | 30527.8 | 30527.8 | 30527.8 | 30527.8
| Sprint 5 | Mar | 29106.8 | 29106.8 | 29106.8 | 29106.8 | 29106.8
| Sprint 6 | Mar | 28232 | 28232 | 28232 | 28232 | 28232
| Sprint 7 | Apr | 29559.4 | 29559.4 | 29559.4 | 29559.4 | 29559.4
| Sprint 8 | Apr | 29920 | 29920 | 29920 | 29920 | 29920
| Total |  | 240882.4 | 240882.4 | 240882.4 | 240882.4 | 240882.4

## sprint 1
Sprint 1
Sprint Number | Sprint Date | Task | Assigned To | Status | Story Point Scale | Reason for Not Completion
1 | Jan 1 - Jan 15 | Create wireframes | Dev A | Completed | 5 | -
|  | Implement responsive design | Dev B | Completed | 8
|  | Integrate Lavie product API | Dev C | Completed | 13
|  | Set up project repository | Dev D | Completed | 3 | -
|  | Initial testing of UI components | Dev E | Completed | 5
budget table :1
| Total Budget | Payment Done | Miscellaneous Expenses | Developer Expenses | Hardware Expenses | Software Expenses | office supplies
| 500000 | 193555 | 36351 | 155136 | 17707 | 24648 | 8179

## sprint 2
Sprint 2
Sprint Number | Sprint Date | Sprint Target | Task | Assigned To | Status | Story Point Scale | Reason for Not Completion
2 | Jan 16 - Jan 31 | Backend API Integration | Develop user login API | Dev A | completed | 8 | -
|  |  | Create shopping cart functionality | Dev B | In Progress | 13 | Complexity of cart logic
|  |  | Implement product listing feature | Dev C | Pending | 8 | Dependencies not resolved
|  |  | Set up database schema | Dev D | completed | 5 | -
|  |  | API testing | Dev E | In Progress | 5 | Incomplete API endpoints
BUDGET TABLE :2
Total Budget | Payment Done | Miscellaneous Expenses | Developer Expenses | Hardware Expenses | Software Expenses | Office Supplies | Total Expense
500000 | 207269 | 41192 | 153445 | 18509 | 23519 | 9756 | 453690

## sprint 3
Sprint 3
Sprint Number | Sprint Date | Sprint Target | Task | Assigned To | Status | Story Point Scale | Reason for Not Completion
3 | Feb 1 - Feb 15 | Payment Gateway Integration | Research payment gateway options | Dev A | Completed | 5 | -
|  |  | Implement payment API | Dev B | completed | 13
|  |  | Frontend payment flow | Dev C | Completed | 8
|  |  | Security testing | Dev D | Completed | 5
|  |  | Error handling and fallback | Dev E | not completed | 5 | Payment vendor delay
BUDGET TABLE :3
Total Budget | Payment Done | Miscellaneous Expenses | Developer Expenses | Hardware Expenses | Software Expenses | Office Supplies | Total Expense
500000 | 192320 | 43254 | 149101 | 23230 | 25990 | 10745 | 444640

## sprint 4
Sprint 4
Sprint Number | Sprint Date | Sprint Target | Task | Assigned To | Status | Story Point Scale | Reason for Not Completion
4 | Feb 16 - Feb 29 | User Profile and Dashboard | Design user profile page | Dev A | Completed | 8
|  |  | Implement dashboard analytics | Dev B | Completed | 13
|  |  | Create user order history | Dev C | Completed | 8
|  |  | Setup notification services | Dev D | Not completed | 5 | SMTP server not responding
|  |  | Testing of dashboard features | Dev E | Completed | 5
BUDGET TABLE:4
Total Budget | Payment Done | Miscellaneous Expenses | Developer Expenses | Hardware Expenses | Software Expenses | Office Supplies | Total Expense
500000 | 210073 | 25219 | 152639 | 23157 | 24127 | 11253 | 446468

## sprint 5
Sprint 5
Sprint Number | Sprint Date | Sprint Target | Task | Assigned To | Status | Story Point Scale | Reason for Not Completion
5 | Mar 1 - Mar 15 | Implement Product Reviews | Design review forms | Dev A | Not completed | 5 | UI design changes
|  |  | Develop review API | Dev B | Completed | 8
|  |  | Integrate review system | Dev C | Completed | 13
|  |  | Test review functionality | Dev D | Completed | 5
|  |  | Deploy review system | Dev E | Completed | 3
BUDGET TABLE:5
Total Budget | Payment Done | Miscellaneous Expenses | Developer Expenses | Hardware Expenses | Software Expenses | Office Supplies | Total Expense
500000 | 191894 | 34128 | 145534 | 21728 | 25200 | 8142 | 426626

## sprint6
Sprint 6
Sprint Number | Sprint Date | Sprint Target | Task | Assigned To | Status | Story Point Scale | Reason for Not Completion
6 | Mar 16 - Mar 31 | Implement Wishlist Feature | Design wishlist UI | Dev A | Completed | 5
|  |  | Develop wishlist API | Dev B | Pending | 8 | Backend workload
|  |  | Integrate wishlist system | Dev C | Completed | 13
|  |  | Testing wishlist functionality | Dev D | Completed | 5
|  |  | Deploy wishlist feature | Dev E | Completed | 3
BUDGET TABLE 6
Total Budget | Payment Done | Miscellaneous Expenses | Developer Expenses | Hardware Expenses | Software Expenses | Office Supplies | Total Expense
500000 | 218454 | 39442 | 141160 | 15591 | 29372 | 11764 | 455783

## sprint 7
Sprint 7
Sprint Number | Sprint Date | Sprint Target | Task | Assigned To | Status | Story Point Scale | Reason for Not Completion
7 | Apr 1 - Apr 15 | Implement Loyalty Program | Design loyalty UI | Dev A | Conpleted | 5
|  |  | Develop loyalty API | Dev B | completed | 8
|  |  | Integrate loyalty system | Dev C | completed | 13
|  |  | Test loyalty features | Dev D | completed | 5
|  |  | Deploy loyalty program | Dev E | Pending | 3 | QA not completed
BUDGET TABLE:7
Total Budget | Payment Done | Miscellaneous Expenses | Developer Expenses | Hardware Expenses | Software Expenses | Office Supplies | Total Expense
500000 | 202103 | 33277 | 147797 | 22898 | 29119 | 11827 | 447021

## sprint 8
Sprint 8
Sprint Number | Sprint Date | Sprint Target | Task | Assigned To | Status | Story Point Scale | Reason for Not Completion
8 | Apr 16 - Apr 30 | Launch and Bug Fixes | Final system testing | Dev A | Completed | 8 | Testing phase extended
|  |  | Performance optimization | Dev B | Completed | 13 | Identified critical issues
|  |  | Deployment to production | Dev C | Completed | 5 | Approval delays
|  |  | Post-launch monitoring setup | Dev D | Completed | 5 | Monitoring tools not configured
|  |  | Marketing feature integration | Dev E | Completed | 5 | Awaiting final assets
BUDGET TABLE 8
Total Budget | Payment Done | Miscellaneous Expenses | Developer Expenses | Hardware Expenses | Software Expenses | Office Supplies | Total Expense
500000 | 182031 | 25840 | 149600 | 19355 | 26940 | 10731 | 414497

## Budget
BUDGET TABLE
Sprint | Month | Developer Expenses | Hardware Expenses | Software Expenses | Office Supplies | Miscellaneous Expenses | Payment Done | Total Expenses
Sprint 1 | January | 155136 | 17707 | 24648 | 8179 | 41192 | 193555 | 440417
Sprint 2 | January | 153445 | 18509 | 23519 | 9756 | 41192 | 207269 | 453690
Sprint 3 | February | 149101 | 23230 | 25990 | 10745 | 43254 | 192320 | 453690
Sprint 4 | February | 152639 | 23157 | 24127 | 11253 | 25219 | 210073 | 444640
Sprint 5 | March | 145534 | 21728 | 25200 | 8142 | 34128 | 191894 | 446468
Sprint 6 | March | 141160 | 15591 | 29372 | 11764 | 39442 | 218454 | 426626
Sprint 7 | April | 147797 | 22898 | 29119 | 11827 | 33277 | 202103 | 455783
Sprint 8 | April | 149600 | 19355 | 26940 | 10731 | 25840 | 182031 | 447021
TOTAL | 1931443